## Slide 1
DGIWG Conference
Amsterdam, NL
24 - 25 April 2005
Services & Interfaces Technical Panel (SITP) Report

## Slide 2: Active SITP Projects
S01 Portrayal Service
S03 Request For Information (RFI) Service Plan
S04 Service Architecture
S05 Web Data Service Access Plan
S07 Catalogue Service
S09 Gazetteer Service
S11 Change Management Service
S12 Web Services Compliance Testing

## Slide 3
  Project Sheet revised by Portrayal Thematic ‘Team’ in conjunction with other DGIWG Portrayal Projects
  Project Lead to be confirmed
  Draft Schedule prepared
S01 Portrayal Service

## Slide 4
  Published on Sitescape after the Madrid Conference.
  Version 6.1 of draft specification issued for comment March 06.
  The NZDF (JGSF) has offered a member to join
  S03 by providing assistance via email, web-casts
  and VTC etc to progress this work.
  Awaiting feedback from NATO on their RFI Management System development to see if there are any impacts to the RFI Spec.
  Vote to resolution to draft standard pending editorial corrections
S03 Request For Information (RFI) Service Plan

## Slide 5
  Expect to publish a draft version of the document in September 06.
  Letter ballot to follow.
S04 Service Architecture
(Creating a structure and roadmap for SITP projects).

## Slide 6
  Important to begin this project.
  Seeking project team lead and additional team members to join the project.
  Potential resources;
    GBR has SMEs and can assign some resources.
    The NZ has offered a member to join the project team by providing assistance via email, web-casts and VTC.
    Norway has indicated that they would like to attend the kick off meeting.
S05 Web Data Service Access Plan

## Slide 7
  The S07 project team meeting will focus on finalizing the profile (OGC).
  Project is progressing well with the objective to have a Draft Standard ready by summer 06 for consideration by DGIWG members.
  Completion dependant on receipt of information from D19 Metadata Project.
  Identified as highest priority in DGIWG survey 2002.
  Requires implementation and testing by Fall 06. Needs linking to existing National Projects – at least two Nation participation plus NATO (Phase 3 Core GIS).
S07 Catalogue Service
(Publish and Find Metadata on Geospatial Resources).

## Slide 8
  Initial meeting held in Spindleruv in Nov 05.
  Follow on meeting held London Jan 06.
  Identified reference documents.
  Reviewed GBR’s Concept of Operations for a Gazetteer document.
  Reviewed OGC’s Gazetteer Service Profile of the
  Web Feature Service Implementation Specification.
  Another year’s effort is required.
S09 Gazetteer Web Service

## Slide 9
  Little progress to date.
  Alignment with IHO and OGC required.
S11 Change Management Service
(Updating of distributed data sets).

## Slide 10
  Still need to engage Defence Information Systems Agency (Phil Hammond) to assist with testing of web based services.
  Possibility of engaging OGC.
  Possibility of engaging America, Britain, Canada, Australia Armies Standardisation Programme (ABCA). NZ Lt Col Bruce Crisp is defining Geospatial requirements (Army based – not a joint requirement) for the Capability Group Sense. ABCA could be used as an independent test bed.
  Authority and further discussion needed before ABCA is approached.
  Approved at the Madrid Plenary.
  Call for resources.
S12 Web Services Compliance Testing

## Slide 11
QUESTIONS?
Contact Karpal Chana
C/SIPT
Head Standards Branch DGI HQ
+44 (0) 208 818 2333
dgi-standardshdc1@dgi.mod.uk